How to use this template Replace the fields in [square brackets], adapt or delete the sample rows, copy or insert rows – and remove this grey box before you share the plan. Tip: print it with date and version so everyone on the day works from the same plan.

Run sheet

Event-day schedule

| Event | [Anniversary party, Sample Ltd] | Date | [Sat, 14 Nov 2026] |
| --- | --- | --- | --- |
| Venue | [Venue, street, postcode, city] | Guests | [120 people] |
| Client contact | [Name, mobile] | Internal contact | [Name, mobile] |
| Event lead on site | [Name, mobile] | Date / version | [10 Nov 2026 · V3] |

| Schedule |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Time | Programme item | Owner | Room / area | Tech / material | Catering note | Status |
| 12:00–13:30 | Furniture and tech delivery | Logistics | Loading bay, hall | Bar tables, stage, PA system | – | confirmed |
| 13:30–14:00 | Catering delivery, connect cooling | Head chef | Kitchen / office | Cooling trailer, 32 A power | Pre-heat warming units | confirmed |
| 14:00–15:30 | Set up buffet line, bar and tables | Service lead | Hall, foyer | Chafing dishes, bar counter | 130 covers, glasses for reception | open |
| 15:30–16:15 | Tech check and sound check | Tech | Stage | 2 wireless mics, projector, laptop | – | open |
| 16:30–17:00 | Briefing service and kitchen team | Event lead | Office | Printed run sheet | Special meals: 6× vegan, 2× gluten-free | open |
| 17:30–18:15 | Doors open, sparkling reception | Service | Foyer | Cloakroom, guest list | Sparkling wine, juice, soft drinks; finger food | open |
| 18:15–18:30 | Welcome by the management | [Client: name] | Stage | Handheld mic, slides | Pause drinks service | open |
| 18:30–19:45 | Buffet opening, main course | Head chef | Hall | – | Hot buffet, refill every 20 min | open |
| 19:45–20:15 | Awards and anniversary speech | [Client: name] | Stage | Projector, music cues | Clear main course | open |
| 20:15–21:00 | Dessert and coffee | Service | Hall | – | Dessert buffet, coffee station | open |
| 21:00–00:30 | Band / DJ, bar service | DJ, bar team | Hall | Lighting, dance floor | Bar service, prepare midnight snack | open |
| 23:00–23:30 | Midnight snack | Kitchen | Foyer | – | Street-food snack, vegetarian option | open |
| 00:30–01:00 | Last orders, farewell | Event lead | Foyer | Cloakroom | Record remaining drinks | open |
| 01:00–03:00 | Breakdown and final cleaning | Logistics, service | All rooms | Van | Count empties, document leftovers | open |

| Emergency and contacts |  |
| --- | --- |
| Emergency number on site | [Name, mobile] |
| Tech supplier | [Company, name, mobile] |
| Venue / facilities | [Name, mobile] |
| Notes | [e.g. delivery window, parking, noise limit from 10 pm] |